## Requirements
| tasks | sub-tasks | member | job % | due date | comment
authorization && authentication (backend + ui) | user signin and signup |  | Byamba | 100 | 2022-07-05 20:00
| jwt token implementation |  |  | 100
| role based authorization |  |  | 100
student (backend + ui) | registration |  | Byamba | 100
| edit profile |  | Ibrahim, Natsnet | 90 | 2022-07-07 20:00 | same as faculty
| add job ads | upload pictures |  | 60
|  | optional use s3 |  | 0
|  | edit job ads |  | 60
| filter job ads | by tags |  | 90 |  | same as faculty
|  | by state |  | 90
|  | by city |  | 90
|  | by companyName |  | 90
| auto-complete tags while typing |  |  | 90
| add professional job expierence |  |  | 60
| display the last 10 job advertisements |  |  | 60 |  | same as faculty
| display 10 most recently applied job advertisements |  |  | 60
| reset password |  |  | 0
faculty (backend + ui) | registration |  | Byamba | 100 | 2022-07-05 20:00
| edit profile |  | Byamba, Lkhagvazaya | 90 | 2022-07-07 20:00 | need to add style profile page
| filter job ads | by tags |  | 95 |  | need to add validation for inputs
|  | by state |  | 95
|  | by city |  | 95
|  | by companyName |  | 95
| filter students | by state |  | 95
|  | by city |  | 95
|  | by major |  | 95
|  | by name |  | 95
|  | by student id |  | 95
| display the last 10 job advertisements |  |  | 50
| display 10 most recently applied job advertisements |  |  | 60
| auto-complete tags while typing |  |  | 100
| comments on students | can write comments on students |  | 90
|  | only faculty can see the comments |  | 90
admin (backend + ui) | change password |  | Byamba | 90% | 2022-07-09 20:00
| activate/deactivate students and faculty |  |  | 90%
Charts | Number of job advertisements per location |  | Lkhagvazaya | 100% | 2022-07-10 20:00
| Number of job students per state |  |  | 100%
| Number of students per city |  |  | 100%
| Tags |  |  | 0
| Tags with location |  |  | 40%
| Average time spent to find a job per gpa range |  |  | 0
| Add at lest 4 more charts as you see fit |  |  | 100
System (backend + ui message) | Optional: Log data before/after for update operations |  |  | 0
| Limit login attempts. If a user try to login with an invalid password more than 5 times, the system will block the user and make it unable to login for 15 minutes |  | Byamba | 100 | 2022-07-10 20:00
| Log all user acitivities on the system |  | Byamba | 100

## Extra mile
| tasks | sub-tasks | member | job % | due date
Authentication & Autherization | OAuth 2.0 and OpenId for autherization and authentication with keyCloak
Notification | AppliedToTheJob: To the owner of the job advertisement when a student has applied to the job. NewJobPoster: To all students who are interested in job poster's tags get a notification about the job.
Create Docker | Create a deployment-ready docker image. |  | Byamba | 100
Chat | Implement a chat feature
2FA | Implement 2 factor authentication. Refer to OTP. |  | Byamba | 100